## Year
Quarter | Goals
Quarter 1 | To have a functional demo
Quarter 2 | Feed database with data
Quarter 3 | Train ML model
Quarter 4 | Deploying the ML model

## Quarter 1
Week |  | Difficulty
2025-01-06 | Create a security scheme | 2
2025-01-13 | Build catalog API | 2
2025-01-20 | Create unit tests | 1
2025-01-27 | Test continuous integration for backend | 2
2025-02-03 | Test continuous delivery for backend | 2
2025-02-10 | Build process API | 3
2025-02-17 | Create unit tests | 1
2025-02-24 | Build API for reports | 2
2025-03-03 | Create unit tests | 1
2025-03-10 | Create UI for catalogs | 2
2025-03-17 | Create UI for processes | 3
2025-03-24 | Create UI for reports | 3
2025-03-31 | Product ready for QA | 1