## Quarter 1
Yearly Plan 2025
Quaterly Plan Q1
Project Name |  |  | PM | Start Date | End Date
House price prediction app |  |  | Azael Vargas | 2025-01-06 | 2025-12-21
Week (Estimation of time) |  |  | Sprint | Release # | Feature | Points | Status
Week 01 | 2025-01-06 | 2025-01-12
Week 02 | 2025-01-13 | 2025-01-19 | Sprint 1 |  | Project setup and CI/CD pipe initialization | 5 | Done
Week 03 | 2025-01-20 | 2025-01-26
Week 04 | 2025-01-27 | 2025-02-02 | Sprint 2 | 1.10 | User registration and login | 8 | Done
Week 05 | 2025-02-03 | 2025-02-09
Week 06 | 2025-02-10 | 2025-02-16 | Sprint 3 |  | Role-based access control | 13 | Done
Week 07 | 2025-02-17 | 2025-02-23
Week 08 | 2025-02-24 | 2025-03-02 | Sprint 4 | 1.20 | Database schema & API setup | 10 | Done
Week 09 | 2025-03-03 | 2025-03-09
Week 10 | 2025-03-10 | 2025-03-16 | Sprint 5 |  | Unit testing framework | 7 | In Progress
Week 11 | 2025-03-17 | 2025-03-23
Week 12 | 2025-03-24 | 2025-03-30 | Sprint 6 | 1.30 | Dashboard with basic UI | 9 | To do
Top 3 Quarter Goals | [5 empty] | Project management guidelines
Establish project scope | [5 empty] | Demo last day of every sprint
Develop core architecture | [5 empty] | Bi-weekly planning after demo
Implement basic authentication | [5 empty] | Consumer / stakeholder release every 4 week
Tickets represent 4 hour - 3 day block of works
Quaterly Plan Q2
Project Name |  |  | PM | Start Date | End Date
House price prediction app |  |  | Azael Vargas | 2025-01-06 | 2025-12-21
Week (Estimation of time) |  |  | Sprint | Release # | Feature | Points | Status
Week 13 | 2025-03-31 | 2025-04-06
Week 14 | 2025-04-07 | 2025-04-13 | Sprint 7 |  | Core business logic | 10 | To do
Week 15 | 2025-04-14 | 2025-04-20
Week 16 | 2025-04-21 | 2025-04-27 | Sprint 8 | 1.40 | UI/UX improvements | 7 | To do
Week 17 | 2025-04-28 | 2025-05-04
Week 18 | 2025-05-05 | 2025-05-11 | Sprint 9 |  | Form validation and error handling | 8 | To do
Week 19 | 2025-05-12 | 2025-05-18
Week 20 | 2025-05-19 | 2025-05-25 | Sprint 10 | 1.50 | Notification system | 10 | To do
Week 21 | 2025-05-26 | 2025-06-01
Week 22 | 2025-06-02 | 2025-06-08 | Sprint 11 |  | External API integration | 12 | To do
Week 23 | 2025-06-09 | 2025-06-15
Week 24 | 2025-06-16 | 2025-06-22 | Sprint 12 | 1.60 | Real-time data synchronization | 13 | To do
Week 25 | 2025-06-23 | 2025-06-29
Week 26 | 2025-06-30 | 2025-07-06 | Sprint 13 |  | Implement payment gateway | 9 | To do
Top 3 Quarter Goals | [5 empty] | Project management guidelines
Implement core business and logic | [5 empty] | Demo last day of every sprint
Enhance UI/UX design an interactivity | [5 empty] | Bi-weekly planning after demo
Integrate external APIs | [5 empty] | Consumer / stakeholder release every 4 week
Tickets represent 4 hour - 3 day block of works
Quaterly Plan Q3
Project Name |  |  | PM | Start Date | End Date
House price prediction app |  |  | Azael Vargas | 2025-01-06 | 2025-12-21
Week (Estimation of time) |  |  | Sprint | Release # | Feature | Points | Status
Week 27 | 2025-07-07 | 2025-07-13
Week 28 | 2025-07-14 | 2025-07-20 | Sprint 14 | 1.70 | Security enhancements (OAuth, encryption) | 11 | To do
Week 29 | 2025-07-21 | 2025-07-27
Week 30 | 2025-07-28 | 2025-08-03 | Sprint 15 |  | Performance optimization | 9 | To do
Week 31 | 2025-08-04 | 2025-08-10
Week 32 | 2025-08-11 | 2025-08-17 | Sprint 16 | 1.80 | Caching & database indexing | 12 | To do
Week 33 | 2025-08-18 | 2025-08-24
Week 34 | 2025-08-25 | 2025-08-31 | Sprint 17 |  | Load testing & debugging | 10 | To do
Week 35 | 2025-09-01 | 2025-09-07
Week 36 | 2025-09-08 | 2025-09-14 | Sprint 18 | 1.90 | Automated deployment and monitoring | 13 | To do
Week 37 | 2025-09-15 | 2025-09-21
Week 38 | 2025-09-22 | 2025-09-28 | Sprint 19 |  | Code refactoring for maintainability | 8 | To do
Top 3 Quarter Goals | [5 empty] | Project management guidelines
Enhance system security and data protection. | [5 empty] | Demo last day of every sprint
Optimize performance and scalability. | [5 empty] | Bi-weekly planning after demo
Conduct extensive testing and debugging. | [5 empty] | Consumer / stakeholder release every 4 week
Tickets represent 4 hour - 3 day block of works
Quaterly Plan Q4
Project Name |  |  | PM | Start Date | End Date
House price prediction app |  |  | Azael Vargas | 2025-01-06 | 2025-12-21
Week (Estimation of time) |  |  | Sprint | Release # | Feature | Points | Status
Week 39 | 2025-09-29 | 2025-10-05
Week 40 | 2025-10-06 | 2025-10-12 | Sprint 20 | 2.00 | Beta release & user testing | 12 | To do
Week 41 | 2025-10-13 | 2025-10-19
Week 42 | 2025-10-20 | 2025-10-26 | Sprint 21 |  | Bug fixes and iteration | 9 | To do
Week 43 | 2025-10-27 | 2025-11-02
Week 44 | 2025-11-03 | 2025-11-09 | Sprint 22 | 2.10 | Final security audit | 10 | To do
Week 45 | 2025-11-10 | 2025-11-16
Week 46 | 2025-11-17 | 2025-11-23 | Sprint 23 |  | Official release & documentation | 11 | To do
Week 47 | 2025-11-24 | 2025-11-30
Week 48 | 2025-12-01 | 2025-12-07 | Sprint 24 | 2.20 | Post-launch analytics setup | 8 | To do
Week 49 | 2025-12-08 | 2025-12-14
Week 50 | 2025-12-15 | 2025-12-21 | Sprint 25 |  | Roadmap for future versions | 7 | To do
Top 3 Quarter Goals | [5 empty] | Project management guidelines
Prepare for production deployment. | [5 empty] | Demo last day of every sprint
Gather user feedback and iterate. | [5 empty] | Bi-weekly planning after demo
Plan long-term sustainability and improvements. | [5 empty] | Consumer / stakeholder release every 4 week
Tickets represent 4 hour - 3 day block of works